## Turret Bearing Replacement
Scenario: Permanent Spread Mooring
| Operations Breakdown | [14 empty] | Base Case Duration & Cost | [5 empty] | Risks |  | Weather Dependency |  |  |  |  | Outages (Mechanical Failures, procurment delays, etc)
| Operation (Level 1) | Operation Label (Level 1) | Predecessor Operation | Start Date | Operational Breakdown (Level 2) | Operational Label (Level 2) | Predecessor Operation | Start Date | Operational Breakdown (Level 3) | Operational Label (Level 3) | Predecessor Operation | Start Date | Operation | Predecessor Operation | Start Date | Base Case Duration, as indicated in Crondall report | Base Case Duration of lower level operations as defined by BPP | Base Case One off cost as per Crondall (USD) | Base Case Dayrate Cost as per Crondall (USD) | Base Case One off cost as per BPP (USD) | Base Case Dayrate Cost as per BPP (USD) | Risks as per Crondal | Risks as per BPP | Weather Dependent (Y/N) | Operations | Forecast Limits for Operation Start | Forecast Lookahead | Operation Durations | Outage Type | PDF Details Durations | PDF Parameters Durations | PDF Details Cost | PDF Parameter Cost | Outage (MTBF/MTTR) | Distribution (normal, etc.) mean and standard deviation | Consider other operational limitations - Flags, etc??
| Rules | [11 empty] | op | pre_op | start_date | day_c | day_b | one_off_c | day_rate_c | one_off_b | day_rate_b | [8 empty] | pdf_type_duration | pdf_parameters_duration | pdf_type_cost | pdf_parameters_cost
Comments | Top level operations for completion of scenario | OP = Offshore Operation; EP = Engineering/Procurement; SY = Shipyard; CS = Continual Service | Start date might be required if we need to consider a delay between the completion of one operation and start of next operation, e.g seasonal operational restrictions, availability of manufacturing facilities, etc. |  | Consider key components within operations and the level to which these need to be broken down (1,2,3,4,…) |  | May be selected from any level of breakdown | [5 empty] | Summary of all operations considered and predecessors. Details to be entered into software. Where both a date and predecessor are indicated for any one operation, software takes latest date. |  |  | Sum of lower level operation durations considered may be lower than base case durations - refer to operation duration section in Weather Dependency | [9 empty] | Sea state, wind, current |  | Software calls up project specific database |  | Choose between exponential, normal, etc. - from PDF selection in software library | [5 empty] | Identify any condition or other operation which may prevent operation proceeding.
| Survey of Wet Storage Areas | OP1 |  | 2017-04-03
[5 empty] | Vessel Mob | OP1-1 |  | 2017-04-03 |  |  |  |  | OP1-1 |  | 2017-04-03 | 3 days | 3 days |  | 99000 |  | 99000
[5 empty] | Sail to site and DP trials | OP1-2 | OP1-1 | 2017-04-06 |  |  |  |  | OP1-2 | OP1-1 | 2017-04-06 | 1 day | 1 day |  | 99000 |  | 99000
[5 empty] | Seabed Survey | OP1-3 | OP1-2 | 2017-04-07 |  |  |  |  | OP1-3 | OP1-2 | 2017-04-07 | 4 days | 4 days |  | 99000 |  | 99000
[5 empty] | Geotechnical Survey | OP1-4 | OP1-2 | 2017-04-07 |  |  |  |  | OP1-4 | OP1-2 | 2017-04-07 | 2 days | 2 days |  | 99000 |  | 99000
[5 empty] | Sail to Port/ Demob | OP1-5 | OP1-3 | 2017-04-13 |  |  |  |  | OP1-5 | OP1-3 | 2017-04-13 | 2 days | 2 days |  | 99000 |  | 99000
| Inspection of Risers & Mooring | OP2 |  | 2017-04-03
[5 empty] | Vessel Mob | OP2-1 |  | 2017-04-03 |  |  |  |  | OP2-1 |  | 2017-04-03 | 3 days | 3 days |  | 99000 |  | 99000
[5 empty] | Sail to Site | OP2-2 | OP2-1 | 2017-04-06 |  |  |  |  | OP2-2 | OP2-1 | 2017-04-06 | 1 day | 1 day |  | 99000 |  | 99000
[5 empty] | Riser Inspection | OP2-3 | OP2-2 | 2017-04-07 |  |  |  |  | OP2-3 | OP2-2 | 2017-04-07 | 4 days | 4 days |  | 99000 |  | 99000
[5 empty] | Mooring Inspection | OP2-4 | OP2-2 | 2017-04-07 |  |  |  |  | OP2-4 | OP2-2 | 2017-04-07 | 3 days | 3 days |  | 99000 |  | 99000
[5 empty] | Sail to Port/ Demob | OP2-5 | OP2-3 | 2017-04-13 |  |  |  |  | OP2-5 | OP2-3 | 2017-04-13 | 2 days | 2 days |  | 99000 |  | 99000
| Engineering of Mooring System & Subsea Operations | EP1 , OP3 |  | 2017-04-03 | [11 empty] | 150 days | - | 2000000
[5 empty] | Engineering of Mooring System | EP1-1 |  | 2017-04-03 |  |  |  |  | EP1-1 |  | 2017-04-03 | - | 75 days |  |  | 1000000
[5 empty] | Subsea Operations | OP3-1 | EP1-1 | [5 empty] | OP3-1 | EP1-1 |  | - | 75 days |  |  | 1000000
| Procurement of Laydown Heads and Protection for the Risers | EP2 |  | 2017-04-03 | [10 empty] | 2017-04-03 | 60 days | 60 days | 2400000 |  | 2400000
| Preparation work on-board FPSO | OP4 |  | 2017-04-03
[5 empty] | Mob of Construction Crew | OP4-1 | EP1-1 | 2017-04-03 |  |  |  |  | OP4-1 | EP1-1 | 2017-04-03 | 4 days | 4 days |  | 11250 |  | 11250
[5 empty] | Inspection of pull-in winch and prep access route for winch wire | OP4-2 | OP4-1 | 2017-04-07 |  |  |  |  | OP4-2 | OP4-1 | 2017-04-07 | 8 days | 8 days |  | 11250 |  | 11250
[5 empty] | Erection of access scaffold in Turret | OP4-3 | OP4-2 | 2017-04-19 |  |  |  |  | OP4-3 | OP4-2 | 2017-04-19 | 4 days | 4 days |  | 11250 |  | 11250
[5 empty] | Installation of temporary pipe work for flowline flooding, including chemical injection facilities | OP4-4 | OP4-3 | 2017-04-25 |  |  |  |  | OP4-4 | OP4-3 | 2017-04-25 | 4 days | 4 days |  | 11250 |  | 11250
| Shutdown | OP5 | OP4-4 | 2017-05-01
[5 empty] | Stop production and fill production flowlines with Dead Crude | OP5-1 | OP4-4 | 2017-05-01 |  |  |  |  | OP5-1 | OP4-4 | 2017-05-01 | 4 days | 4 days |  | 0 |  | 0
[5 empty] | Depressurise all flowlines and risers | OP5-2 | OP5-1 | 2017-05-05 |  |  |  |  | OP5-2 | OP5-1 | 2017-05-05 | 2 days | 2 days |  | 0 |  | 0
| Disconnet and Wet Storage of Risers | OP6 | OP5-2 | 2017-05-09
[5 empty] | Disconnect pipe work from risers in turret and fit laydown heads and protection | OP6-1 | OP5-2, EP2 | 2017-05-09 |  |  |  |  | OP6-1 | OP5-2, EP2 | 2017-05-09 | 16 days | 16 days |  | 11250 |  | 11250
[5 empty] | Mob Construction Vessels | OP6-2 | OP5-2 | 2017-05-09 |  |  |  |  | OP6-2 | OP5-2 | 2017-05-09 | 3 days | 3 days |  | 198000 |  | 198000
[5 empty] | Sail to site and DP trials | OP6-3 | OP6-2 | 2017-05-12 |  |  |  |  | OP6-3 | OP6-2 | 2017-05-12 | 1 day | 1 day |  | 198000 |  | 198000
[5 empty] | Disconnect risers from turret and lay on seabed in wet storage areas | OP6-4 | OP6-1, OP6-3 | 2017-05-31 |  |  |  |  | OP6-4 | OP6-1, OP6-3 | 2017-05-31 | 32 days | 32 days |  | 209250 |  | 209250
| Disconnect and remove mooring lines | OP7 | OP6-4 | 2017-07-14
[5 empty] | Disconnect mooring lines and lay on the seabed | OP7-1 | OP6-4 | 2017-07-14 |  |  |  |  | OP7-1 | OP6-4 | 2017-07-14 | 18 days | 18 days |  | 209250 |  | 209250
[5 empty] | Hook-up of Station Keeping Tugs to FPSO | OP7-2 | OP6-4 | 2017-07-14 |  |  |  |  | OP7-2 | OP6-4 | 2017-07-14 | 8 days | 8 days |  | 128000 |  | 128000
[5 empty] | Station keeping of FPSO during mooring disconnection operation | OP7-3 | OP7-2 | 2017-07-14 |  |  |  |  | OP7-3 | OP7-2 | 2017-07-14 | 18 days | 18 days |  | 128000 |  | 128000
[5 empty] | Disconnect mooring lines subsea and recover to Construction Vessel | OP7-4 | OP7-1 | 2017-08-23 |  |  |  |  | OP7-4 | OP7-1 | 2017-08-23 | 18 days | 18 days |  | 198000 |  | 198000
[5 empty] | Construction Vessel sail to port and demob | OP7-5 | OP7-4 | 2017-09-18 |  |  |  |  | OP7-5 | OP7-4 | 2017-09-18 | 4 days | 4 days |  | 198000 |  | 198000
| Procurement and Installation of new mooring lines and top chain; | EP3 , OP8 |  | 2017-05-15
[5 empty] | Procurement of replacement mooring components | EP3-1 | EP1-1 | 2017-05-15 |  |  |  |  | EP3-1 | EP1-1 | 2017-05-15 | 180 days | 180 days | 10000000 |  | 10000000
[5 empty] | Mob Construction Vessel | OP8-1 | EP3-1 | 2018-01-22 |  |  |  |  | OP8-1 | EP3-1 | 2018-01-22 | 4 days | 4 days |  | 198000 |  | 198000
[5 empty] | Sail to site and DP trials | OP8-2 | OP8-1 | 2018-01-26 |  |  |  |  | OP8-2 | OP8-1 | 2018-01-26 | 1 days | 1 days |  | 198000 |  | 198000
[5 empty] | Install mooring lines and lay on seabed | OP8-3 | OP8-2 | 2018-01-29 |  |  |  |  | OP8-3 | OP8-2 | 2018-01-29 | 27 days | 27 days |  | 198000 |  | 198000
[5 empty] | Demob Construction Vessels | OP8-4 | OP8-3 | 2018-03-07 |  |  |  |  | OP8-4 | OP8-3 | 2018-03-07 | 2 days | 2 days |  | 198000 |  | 198000
| Wet tow FPSO to shipyard (Singapore) | OP9, SY1 | OP7-5 | 2017-09-22
[5 empty] | West Africa to Jubilee - mobilisation | OP9-1 | OP7-4 | 2017-09-22 |  |  |  |  | OP9-1 | OP7-4 | 2017-09-22 | 1 day | 1 day | 90000 |  | 90000
[5 empty] | Jubilee to Singapore - tow | OP9-2 | OP9-1 | 2017-09-25 |  |  |  |  | OP9-2 | OP9-1 | 2017-09-25 | 43 days | 43 days | 7170000 |  | 7170000
[5 empty] | Yard entry prep, de-muck etc | SY1-1 | OP9-1 | 2017-11-01 |  |  |  |  | SY1-1 | OP9-1 | 2017-11-01 | 16 days | 16 days | 1500000 |  | 1500000
| Erect scaffold | SY2 | SY1-1 | 2017-11-23 | [8 empty] | SY2 | SY1-1 | 2017-11-23 | 7 days | 7 days | 66970 |  | 66970
| Cut off turret head | SY3 | SY1-1 | 2017-11-23
[5 empty] | Asian Hercules hire | SY3-1 | SY1-1 | 2017-11-23 |  |  |  |  | SY3-1 | SY1-1 | 2017-11-23 | 2 days | 2 days |  | 200000 |  | 200000
[5 empty] | Cut off turret head | SY3-2 | SY1-1 | 2017-11-23 |  |  |  |  | SY3-2 | SY1-1 | 2017-11-23 | 2 days | 2 days | 23550 |  | 23550
| Install new turret head | SY4 | SY3-1 , SY3-2 | 2017-11-25 | [10 empty] | 2017-11-29
[5 empty] | Lift and attach new turret head | SY4-1 | SY3-1, SY3-2 | 2017-11-25 |  |  |  |  | SY4-1 | SY3-1, SY3-2 | 2017-11-25 | 2 days | 2 days | see note 1 | see note 1 | see note 1 | see note 1
[5 empty] | Asian Hercules hire | SY4-2 | SY3-1, SY3-2 | 2017-11-25 |  |  |  |  | SY4-2 | SY3-1, SY3-2 | 2017-11-25 | 2 days | 2 days
| Re commission turret | SY5 | SY4-2 | 2018-04-21 | [8 empty] | SY5 | SY4-2 | 2018-04-21 | 14 days | 14 days | 64889 |  | 64889
| Yard services | SY6 | SY5 | 2017-11-23 | [8 empty] | SY6 | SY5 | 2017-11-23 |  |  | 8875364 |  | 8875364
| Wet tow of FPSO from Singapore to Jubilee field | OP10 | SY6 | 2018-05-03
[5 empty] | Singapore to Jubilee - tow | OP10-1 | SY6 | 2018-05-03 |  |  |  |  | OP10-1 | SY6 | 2018-05-03 | 43 days | 43 days | 7170000 |  | 7170000
[5 empty] | Jubilee to Singapore demobilisation | OP10-2 | OP10-1 | 2018-05-03 |  |  |  |  | OP10-2 | OP10-1 | 2018-05-03 | 31 days | 31 days | 2940000 |  | 2940000
| RE-Installation of FPSO | OP11 |  | 2018-06-27
[5 empty] | Hook-up of Station Keeping Tugs to FPSO | OP11-1 | OP10-1 | 2018-06-29 |  |  |  |  | OP11-1 | OP10-1 | 2018-06-29 | 2 days | 2 days |  | 128000 |  | 128000
[5 empty] | Mob of Construction Crew | OP11-2 | OP10-1 | 2018-06-27 |  |  |  |  | OP11-2 | OP10-1 | 2018-06-27 | 4 days | 4 days |  | 11250 |  | 11250
[5 empty] | Mob Construction Vessels | OP11-3 | OP10-1 | 2018-06-27 |  |  |  |  | OP11-3 | OP10-1 | 2018-06-27 | 4 days | 4 days |  | 198000 |  | 198000
[5 empty] | Sail to site and DP trials | OP11-4 | OP10-1 , OP11-1 , OP11-2 , OP11-3 | 2018-07-03 |  |  |  |  | OP11-4 | OP10-1 , OP11-1 , OP11-2 , OP11-3 | 2018-07-03 | 1 day | 1 day |  | 198000 |  | 198000
[5 empty] | Recover mooring lines from seabed and connect to FPSO | OP11-5 | OP11-4 | 2018-07-04 |  |  |  |  | OP11-5 | OP11-4 | 2018-07-04 | 18 days | 18 days |  | 209250 |  | 209250
[5 empty] | Station keeping of FPSO during mooring connection operation | OP11-6 | OP10-1 , OP11-1 , OP11-2 , OP11-3 | 2018-07-03 |  |  |  |  | OP11-6 | OP10-1 , OP11-1 , OP11-2 , OP11-3 | 2018-07-03 | 18 days | 18 days |  | 128000 |  | 128000
[5 empty] | Recover risers from seabed and connect to turret | OP11-7 | OP11-5 | 2018-07-30 |  |  |  |  | OP11-7 | OP11-5 | 2018-07-30 | 32 days | 32 days |  | 209250 |  | 209250
[5 empty] | FPSO heading control during riser pull-in | OP11-8 | OP11-5 | 2018-07-30 |  |  |  |  | OP11-8 | OP11-5 | 2018-07-30 | 32 days | 32 days |  | 72000 |  | 72000
[5 empty] | Recommission Subsea Control System | OP11-9 | OP11-7 , OP11-8 | 2018-09-12 |  |  |  |  | OP11-9 | OP11-7 , OP11-8 | 2018-09-12 | 6 days | 6 days |  | 198000 |  | 198000
[5 empty] | Demob Construction Vessels | OP11-10 | OP11-7 , OP11-8 | 2018-09-12 |  |  |  |  | OP11-10 | OP11-7 , OP11-8 | 2018-09-12 | 2 days | 2 days |  | 198000 |  | 198000
[5 empty] | Demob Heading Control Tugs | OP11-11 | OP11-7 , OP11-8 | 2018-09-12 |  |  |  |  | OP11-11 | OP11-7 , OP11-8 | 2018-09-12 | 2 days | 2 days |  | 72000 |  | 72000
| Hookup and flush risers | OP12 | OP11-7 , OP11-8 | 2018-09-12
[5 empty] | Reconnect and test pipe work to risers in turret | OP12-1 | OP11-7 , OP11-8 | 2018-09-12 |  |  |  |  | OP12-1 | OP11-7 , OP11-8 | 2018-09-12 | 24 days | 24 days |  | 11250 |  | 11250
[5 empty] | Dismount temporary pipe work and scaffolding | OP12-2 | OP12-1 | 2018-10-16 |  |  |  |  | OP12-2 | OP12-1 | 2018-10-16 | 4 days | 4 days |  | 11250 |  | 11250
[5 empty] | Start up production and flush flowlines and risers | OP12-3 | OP12-1 | 2018-10-16 |  |  |  |  | OP12-3 | OP12-1 | 2018-10-16 | 4 days | 4 days |  | 0 |  | 0
[5 empty] | Demob Construction Crew | OP12-4 | OP12-2 , OP12-3 | 2018-10-22 |  |  |  |  | OP12-4 | OP12-2 , OP12-3 | 2018-10-22 | 4 days | 4 days |  | 11250 |  | 11250
| Re commission systems and start up production | OP13 | OP12-2 , OP12-3 | 2018-10-22 | [8 empty] | OP13 | OP12-2 , OP12-3 | 2018-10-22 | 60 days | 60 days |  | 40000 |  | 40000
Install new turret head
|  | Cost of fabrication and installation | [13 empty] | 170 days (?) | 170 days | 3500000 |  | 3500000
|  | Cost or OFE TMS ex swivel and manifold deck | [13 empty] | 335 days (11 months?) | 335 days (11 months?) | 40000000 |  | 40000000
| Cost uplift due to inefficiencies | [16 empty] | 1913063 |  | 1913063
| Indirect costs | [16 empty] | 4883000 |  | 4883000
| Yard services | [16 empty] | 1151303 |  | 1151303
Note on Q36: Ferdinando Samona: This is 28 in the schedule, but 18 in the cost. TO CE CHECKED
Note on C41: Ferdinando Samona: It starts on 15th May. Not sure which is the predecessor operation
Note on F45: Juan Murillo Gonzalez: Polyester ropes should not be set down on the seabed
Note on B59: Ferdinando Samona: Included both "Indirect costs" and "Yard Services" (costs have been summed), Excluded "Cost uplift due to inefficiencies". See Appendix C point 22.0
Note on S59: Ferdinando Samona: Sum of "Indirect costs" and "Yard Services". See Appendix C point 22.0
Note on U59: Ferdinando Samona: Sum of "Indirect costs" and "Yard Services". See Appendix C point 22.0

## Operations Summary
Scenario: Permanent Spread Mooring
Operations Summary
Hardware Requirements | Oil Offloading Line (OOL) Offloading Buoy (OLB) FPSO Reconfiguration Booster Pumps/Heaters Mooring Line Components Dual Axis Chain Stoppers
Offshore Operations | Survey OCV
Additional Cost | Classification Services MWS
Base Case Weather
Initial conditions - e.g tank levels, etc. | FPSO in temporary spread moored condition