## Permanent Spread Mooring
Black color indicates that the information comes from the Crandall cost and schedule estimation
Red color highlights a Crandall information which may need clarification (see comment in the cell for details)
Blue color indicates that the information has been added by BPP
Scenario: Permanent Spread Mooring
| Operations Breakdown | [14 empty] | Base Case Duration & Cost | [5 empty] | Risks |  | Weather Dependency |  |  |  |  | Outages (Mechanical Failures, procurment delays, etc)
| Operation (Level 1) | Operation Label (Level 1) | Predecessor Operation | Start Date | Operational Breakdown (Level 2) | Operational Label (Level 2) | Predecessor Operation | Start Date | Operational Breakdown (Level 3) | Operational Label (Level 3) | Predecessor Operation | Start Date | Operation | Predecessor Operation | Start Date | Base Case Duration, as indicated in Crondall report | Base Case Duration of lower level operations as defined by BPP | Base Case One off cost as per Crondall (USD) | Base Case Dayrate Cost as per Crondall (USD) | Base Case One off cost as per BPP (USD) | Base Case Dayrate Cost as per BPP (USD) | Risks as per Crondal | Risks as per BPP | Weather Dependent (Y/N) | Operations | Forecast Limits for Operation Start | Forecast Lookahead | Operation Durations | Outage Type | PDF Details | Outage (MTBF/MTTR) | Distribution (normal, etc.) mean and standard deviation | Consider other operational limitations - Flags, etc??
| Rules | [11 empty] | op | pre_op | start_date | day_c | day_b | one_off_c | day_rate_c | one_off_b | day_rate_b
Comments | Top level operations for completion of scenario | OP = Offshore Operation; EP = Engineering/Procurement; SY = Shipyard; CS = Continual Service | Start date might be required if we need to consider a delay between the completion of one operation and start of next operation, e.g seasonal operational restrictions, availability of manufacturing facilities, etc. |  | Consider key components within operations and the level to which these need to be broken down (1,2,3,4,…) |  | May be selected from any level of breakdown | [5 empty] | Summary of all operations considered and predecessors. Details to be entered into software. Where both a date and predecessor are indicated for any one operation, software takes latest date. |  |  | Sum of lower level operation durations considered may be lower than base case durations - refer to operation duration section in Weather Dependency | [9 empty] | Sea state, wind, current |  | Software calls up project specific database |  | Choose between exponential, normal, etc. - from PDF selection in software library |  |  | Identify any condition or other operation which may prevent operation proceeding.
| Survey for OLB | OP1 |  | 2017-04-03
[5 empty] | Vessel Mob | OP1-1 |  | 2017-04-03 |  |  |  |  | OP1-1 |  | 2017-04-03 | 3 | 3 |  | 99000 |  | 99000
[5 empty] | Sail to Site and DP trials | OP1-2 | OP1-1 | 2017-04-06 |  |  |  |  | OP1-2 | OP1-1 | 2017-04-06 | 1 | 1 |  | 99000 |  | -
[5 empty] | Seabed Survey | OP1-3 | OP1-2 | 2017-04-07 |  |  |  |  | OP1-3 | OP1-2 | 2017-04-07 | 2 | 2 |  | 99000
[5 empty] | Geotechnical Survey | OP1-4 | OP1-2 | 2017-04-07 |  |  |  |  | OP1-4 | OP1-2 | 2017-04-07 | 3 | 3 |  | 99000 |  | 99000
[5 empty] | Sail to Port/ Demob | OP1-5 | OP1-3 , OP1-4 | 2017-04-13 |  |  |  |  | OP1-5 | OP1-3 , OP1-4 | 2017-04-13 | 2 | 2 |  | 99000 |  | 99000
| Hang-off Structure fabrication | EP1 |  | 2018-07-17 | [8 empty] | EP1 |  | 2018-07-17 | 200 | 200 | 5250000 |  | 5250000
| EPCI for offloading system OLB/OOL | EP2 |  | 2017-04-03 | [8 empty] | EP2 |  | 2017-04-03 | 700 | 700 | 155000000 |  | 155000000 |  | MEDIUM | MEDIUM
| FPSO preparation work for OOL installation | OP2 | EP1 | 2018-02-09 | [13 empty] | -
[5 empty] | CSV Mob | OP2-1 | EP1 | 2018-01-18 |  |  |  |  | OP2-1 | EP1 | 2018-01-18 | 3 | 3 |  | 105000 |  | 105000
[5 empty] | Sail to Site and DP trials | OP2-2 | OP2-1 | 2018-01-23 |  |  |  |  | OP2-2 | OP2-1 | 2018-01-23 | 1 | 1 |  | 105000 |  | -
[5 empty] | Set up at FPSO and transfer construction crew | OP2-3 | OP2-2 | 2018-01-24 |  |  |  |  | OP2-3 | OP2-2 | 2018-01-24 | 1 | 1 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Lift on new Offloading Station | OP2-4 | OP2-3 | 2018-01-25 |  |  |  |  | OP2-4 | OP2-3 | 2018-01-25 | 2 | 2 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Relocate Offloading Hose | OP2-5 | OP2-4 | 2018-01-30 |  |  |  |  | OP2-5 | OP2-4 | 2018-01-30 | 1 | 1 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Remove original Offloading Station | OP2-6 | OP2-5 | 2018-01-31 |  |  |  |  | OP2-6 | OP2-5 | 2018-01-31 | 1 | 1 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Remove hawser reel, mooring winch, deck rollers | OP2-7 | OP2-6 | 2018-02-01 |  |  |  |  | OP2-7 | OP2-6 | 2018-02-01 | 2 | 2 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Relocate pull-in winch, HPU, & sheaves | OP2-8 | OP2-7 | 2018-02-05 |  |  |  |  | OP2-8 | OP2-7 | 2018-02-05 | 2 | 2 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Sail to Port and demob | OP2-9 | OP2-8 | 2018-02-07 |  |  |  |  | OP2-9 | OP2-8 | 2018-02-07 | 2 | 2 |  | 105000 |  | 105000
| OOL Hang-Off Structure Installation | OP3 | EP1, OP2-9 | 2018-02-09
[5 empty] | CSV Mob | OP3-1 | EP1, OP2-9 | 2018-02-09 |  |  |  |  | OP3-1 | EP1, OP2-9 | 2018-02-09 | 3 | 3 |  | 105000 |  | 105000
[5 empty] | Sail to Site and DP trials | OP3-2 | OP3-1 | 2018-02-14 |  |  |  |  | OP3-2 | OP3-1 | 2018-02-14 | 1 | 1 |  | 105000 |  | -
[5 empty] | Set up at FPSO and transfer construction crew | OP3-3 | OP3-2 | 2018-02-15 |  |  |  |  | OP3-3 | OP3-2 | 2018-02-15 | 1 | 1 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Option 1: lifting module support stools | OP3-4 | OP3-3 | 2018-02-16 |  |  |  |  | OP3-4 | OP3-3 | 2018-02-16 | 1 | 1 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Option 1: fit up and welding module support stools | OP3-5 | OP3-4 | 2018-02-19 |  |  |  |  | OP3-5 | OP3-4 | 2018-02-19 | 5 | 5 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Option 1: lifting and securing Hang-Off structure | OP3-6 | OP3-5 | 2018-02-26 |  |  |  |  | OP3-6 | OP3-5 | 2018-02-26 | 2 | 2 |  | 105000 |  | 105000 | MEDIUM | MEDIUM
[5 empty] | Sail to Port and demob | OP3-7 | OP3-6 | 2018-02-28 |  |  |  |  | OP3-7 | OP3-6 | 2018-02-28 | 2 | 2 |  | 105000 |  | 105000
| Installation of mooring lines | OP5 | EP4, EP5 | [9 empty] | OP5 | OP3
| Testing and Commissioning of Offloading System | OP6 | OP2, OP3, OP4 | [9 empty] | OP6 | OP2, OP3, OP4, OP3, |  | 3 | 3 | 30000 |  | 30000
| Classification/Certification Service (for EPCI for Offloading System) | CS1 | OP6 | [9 empty] | CS1 | OP1 |  |  |  | 775000 |  | 775000
| Continue to operate in permanent spread moorings | CS2 | OP5, CS1
| Marine Warranty Services | [16 empty] | 250000 |  | 250000
| Marine Warranty Services |  |  | Date to be defined - start of offshore operation planning | [8 empty] | CS2 |  | Date to be defined - start of offshore operation planning | 200 | 200 | 387500 |  | 387500
Note on F12: Ferdinando Samona: In repair cost and schedule breakdowns (Appendix C, page 55) there is "vessel Mob" 3 days duration and 297k$ cost. This is missing in the project schedule (Appendix B, page 46). Should this be added?
Note on I12: Ferdinando Samona:
Note on I13: Ferdinando Samona: Date in the Crandall schedule estimation is 3th April, but this has been modified to be consistent with the "vessel Mob" reported in the Crandall cost estimation
Note on I14: Ferdinando Samona: Date in the Crandall schedule estimation is 3th April, but this has been modified to be consistent with the "vessel Mob" reported in the Crandall cost estimation
Note on I15: Ferdinando Samona: Date in the Crandall schedule estimation is 3th April, but this has been modified to be consistent with the "vessel Mob" reported in the Crandall cost estimation
Note on I16: Ferdinando Samona: Date in the Crandall schedule estimation is 3th April, but this has been modified to be consistent with the "vessel Mob" reported in the Crandall cost estimation
Note on B18: Ferdinando Samona: BPP added installation of OLB separately (see below)
Note on W18: Ferdinando Samona: Identified as risk D.1 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on E19: Ferdinando Samona: before the end of the EP2
Note on F20: Ferdinando Samona: In repair cost and schedule breakdowns (Appendix C, page 55) there is "vessel Mob" 3 days duration and 297k$ cost. This is missing in the project schedule (Appendix B, page 46). Should this be added?
Note on I20: Ferdinando Samona: 200 days after EP1
Note on W22: Ferdinando Samona: Identified as risk B.1 and B.2 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on W23: Ferdinando Samona: Identified as risk B.1 and B.2 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on W24: Ferdinando Samona: Identified as risk B.1 and B.2 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on W25: Ferdinando Samona: Identified as risk B.1 and B.2 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on W26: Ferdinando Samona: Identified as risk B.1 and B.2 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on W27: Ferdinando Samona: Identified as risk B.1 and B.2 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on E29: Ferdinando Samona: 200 days after EP1
Note on F30: Ferdinando Samona: In repair cost and schedule breakdowns (Appendix C, page 55) there is "vessel Mob" 3 days duration and 297k$ cost. This is missing in the project schedule (Appendix B, page 46). Should this be added?
Note on I30: Ferdinando Samona: 200 days after EP1
Note on W32: Ferdinando Samona: Identified as risk B.3 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on W33: Ferdinando Samona: Identified as risk B.3 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on W34: Ferdinando Samona: Identified as risk B.3 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on W35: Ferdinando Samona: Identified as risk B.3 (see "Risk Assessment (From G-TUL-21-REP-M-Z-050-B1-v6).xlsx")
Note on B42: Ferdinando Samona: Is this related to FPSO preparatory works? See Crandall cost "G-TUL-21-REP-M-Z-050-B1-v6.pdf" page 55
Note on B43: Ferdinando Samona: Is this related to EPCI for Offloading System? See Crandall cost "G-TUL-21-REP-M-Z-050-B1-v6.pdf" page 56

## Operations Summary
Scenario: Permanent Spread Mooring
Operations Summary
Hardware Requirements | Oil Offloading Line (OOL) Offloading Buoy (OLB) FPSO Reconfiguration Booster Pumps/Heaters Mooring Line Components Dual Axis Chain Stoppers
Offshore Operations | Survey OCV
Additional Cost | Classification Services MWS
Base Case Weather
Initial conditions - e.g tank levels, etc. | FPSO in temporary spread moored condition