## Permanent Spread Mooring
Scenario: Permanent Spread Mooring
| Operations Breakdown | [14 empty] | Base Case Duration & Cost | [5 empty] | Risks |  | Weather Dependency |  |  |  |  | Outages (Mechanical Failures, procurment delays, etc)
| Operation (Level 1) | Operation Label (Level 1) | Predecessor Operation | Start Date | Operational Breakdown (Level 2) | Operational Label (Level 2) | Predecessor Operation | Start Date | Operational Breakdown (Level 3) | Operational Label (Level 3) | Predecessor Operation | Start Date | Operation | Predecessor Operation | Start Date | Base Case Duration, as indicated in Crondall report | Base Case Duration of lower level operations as defined by BPP | Base Case One off cost as per Crondall (USD) | Base Case Dayrate Cost as per Crondall (USD) | Base Case One off cost as per BPP (USD) | Base Case Dayrate Cost as per BPP (USD) | Risks as per Crondal | Risks as per BPP | Weather Dependent (Y/N) | Operations | Forecast Limits for Operation Start | Forecast Lookahead | Operation Durations | Outage Type | PDF Details | Outage (MTBF/MTTR) | Distribution (normal, etc.) mean and standard deviation | Consider other operational limitations - Flags, etc??
Rules
Comments | Top level operations for completion of scenario | OP = Offshore Operation; EP = Engineering/Procurement; SY = Shipyard; CS = Continual Service | Start date might be required if we need to consider a delay between the completion of one operation and start of next operation, e.g seasonal operational restrictions, availability of manufacturing facilities, etc. |  | Consider key components within operations and the level to which these need to be broken down (1,2,3,4,…) |  | May be selected from any level of breakdown | [5 empty] | Summary of all operations considered and predecessors. Details to be entered into software. Where both a date and predecessor are indicated for any one operation, software takes latest date. |  |  | Sum of lower level operation durations considered may be lower than base case durations - refer to operation duration section in Weather Dependency | [9 empty] | Sea state, wind, current |  | Software calls up project specific database |  | Choose between exponential, normal, etc. - from PDF selection in software library |  |  | Identify any condition or other operation which may prevent operation proceeding.
| Survey for OLB | OP1 |  | 2017-04-03 | [8 empty] | OP1 |  |  | 11 days |  |  | 99000 |  | 99000
| Hang-off Structure fabrication | EP0 |  |  | OP1 | [7 empty] | EP0 | OP1 |  | 200 days |  | 5250000 |  | 5250000
| Engineering/ Procurement OLB/OOL | EP1 | OP1 |  | OP1 | [7 empty] | EP1 | OP1 |  | 700 days |  | 155000000 |  | 155000000 |  | MEDIUM | MEDIUM | N | [5 empty] | Normal distribution |  | Mean = 703 days Standard deviation = 5%
| Engineering/ Procurement Booster Pumps and Heaters | EP2 | OP1 |  | OP1 | [7 empty] | EP2 | OP1 |  | ? | ? | - |  | ? |  | MEDIUM | MEDIUM
| Engineering/ Procurement Mooring Lines | EP3 | OP1 |  | OP1 | [7 empty] | EP3 | OP1 |  | ? | ? | - |  | ?
| Engineering/ Procurement Dual Axis Chain Stoppers | EP4 | OP1 |  | OP1 | [7 empty] | EP4 | OP1 |  | ? | ? | - |  | ? |  | HIGH | HIGH
| Installation of OPB | OP2 | EP1 |  | EP1 | [7 empty] | OP2 | EP1 |  | ? | ? | - |  | ? |  | MEDIUM | MEDIUM
| FPSO preparation work | OP3 | EP2, EP4 | 2017-07-17 | EP2, EP4 | [7 empty] | OP3 | EP2, EP4 | 2017-07-17 | 15 days |  |  | 105000 |  | 105000
| OOL Hang-Off Structure Installation | OP4 |  |  | EP0, OP3 | [7 empty] | OP4 | EP0, OP3 |  | 15 days |  |  | 105000 |  | 105000
| Installation of mooring lines | OP5 | OP3 |  | OP3 | [7 empty] | OP5 | OP3 |  | ? | ? | - |  | ? |  | HIGH | HIGH
| Testing and Commissioning of Offloading System | OP6 | OP2, OP3, OP4 |  | OP2, OP3, OP4 ,OP3, | [7 empty] | OP6 | OP2, OP3, OP4 ,OP3, |  | 3 days |  | 30000 |  | 30000
| Classification/Certification Service | CS1 | OP1 |  | OP1 | [7 empty] | CS1 | OP1 |  |  |  | 775000 |  | 775000
| Marine Warranty Services | CS2 |  | Date to be defined - start of offshore operation planning | [8 empty] | CS2 |  | Date to be defined - start of offshore operation planning | 200 days |  | 387500 |  | 387500
| Marine Warranty Services | [16 empty] | 250000 |  | 250000
Note on W9: Ferdinando Samona: Related Risk ID: D.1
Note on X9: Ferdinando Samona: Related Risk ID: D.1
Note on W12: Ferdinando Samona: Related Risk ID: B.1
Note on X12: Ferdinando Samona: Related Risk ID: B.1
Note on W16: Ferdinando Samona: Related Risck ID A.2
Note on X16: Ferdinando Samona: Related Risck ID A.2
Note on B18: Ferdinando Samona: Is OPB meant to be OLB?. Is it a typo?
Note on W18: Ferdinando Samona: Related Risk ID: B.3
Note on X18: Ferdinando Samona: Related Risk ID: B.3
Note on W24: Ferdinando Samona: Related Risck ID A.2 and A.3
Note on X24: Ferdinando Samona: Related Risck ID A.2 and A.3, but high risk of A.2 considered here

## Operations Summary
Scenario: Permanent Spread Mooring
Operations Summary
Hardware Requirements | Oil Offloading Line (OOL) Offloading Buoy (OLB) FPSO Reconfiguration Booster Pumps/Heaters Mooring Line Components Dual Axis Chain Stoppers
Offshore Operations | Survey OCV
Additional Cost | Classification Services MWS
Base Case Weather
Initial conditions - e.g tank levels, etc. | FPSO in temporary spread moored condition